## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
D-01 | Not recorded | Not recorded | Google Docs (Skia) PDFs were extracted one word per line, so capitalised words became 'projects'. | P5 | jeswinjarald-hash (sole Git author) | Logical | Page text rebuilt from text-run positions when plain text is word-fragmented (pdf_extraction.py). | 2026-10-10 | Closed | RESUME_PARSING_AUDIT.md #1; fix 4699c7c; tests test_pdf_extraction.py, skia_pdf_fixture.py
D-02 | Not recorded | Not recorded | A blank line was an unconditional project boundary and every block's first line became a title ('Built', 'HTML,'). | P5 | jeswinjarald-hash (sole Git author) | Logical | Blocks start a project only when the first line reads as a title; wrapped connector lines rejoined. | 2026-10-10 | Closed | RESUME_PARSING_AUDIT.md #2; fix 4699c7c; test_resume4_regressions.py
D-03 | Not recorded | Not recorded | All-caps lines (dates, '(OOP)', certification lines) were accepted as section headings; certifications and languages were lost. | P5 | jeswinjarald-hash (sole Git author) | Logical | Stricter custom-heading rules (no digits, followed by content, not the name line). | 2026-10-10 | Closed | RESUME_PARSING_AUDIT.md #3; fix 4699c7c; test_section_detection.py
D-04 | Not recorded | Not recorded | DOCX text boxes and page headers were ignored, losing sidebar skills and contact details. | P5 | jeswinjarald-hash (sole Git author) | Logical | Page headers and floating text boxes extracted (docx_extraction.py). | 2026-10-10 | Closed | RESUME_PARSING_AUDIT.md #4; fix 4699c7c; test_docx_extraction.py, docx_layout_fixture.py
D-05 | Not recorded | Not recorded | Ligatures, zero-width characters, soft hyphens and non-breaking spaces were not normalised. | P5 | jeswinjarald-hash (sole Git author) | Logical | Normalisation added in text_utils.py. | 2026-10-10 | Closed | RESUME_PARSING_AUDIT.md #5; fix 4699c7c
D-06 | Not recorded | Not recorded | Fragment project records were cited as evidence in recommendations, customization and interview questions. | P5 | jeswinjarald-hash (sole Git author) | Logical | Shared is_reliable_project rule; unreliable records kept but excluded from evidence. | 2026-10-10 | Closed | RESUME_PARSING_AUDIT.md #6; fix 4699c7c
D-07 | Not recorded | Not recorded | Grounding check passed' was shown for unreliable structure; invented technologies, degrees and employers were not caught; user edits were not re-validated. | P5 | jeswinjarald-hash (sole Git author) | Logical | check_unsupported_claims added; no pass while parser warnings exist; 409 when only fragments remain; edits re-validated. | 2026-10-10 | Closed | RESUME_PARSING_AUDIT.md #7; fix 4699c7c; test_customization_validator.py
D-08 | Not recorded | Not recorded | An unhandled HTTP 500 had no CORS headers, so the Skill Gap page reported a connection failure. | P5 | jeswinjarald-hash (sole Git author) | Logical | Unhandled exceptions become logged JSON 500s inside the CORS layer. | 2026-10-10 | Closed | RESUME_PARSING_AUDIT.md #8; fix 4699c7c
D-09 | Not recorded | Not recorded | Concurrent generation requests violated a UNIQUE constraint (HTTP 500 in 4 of 60 probe requests). | P5 | jeswinjarald-hash (sole Git author) | Logical | Customization and interview version allocation retries on conflict. | 2026-10-10 | Closed | RESUME_PARSING_AUDIT.md #9; fix 4699c7c
D-10 | Not recorded | Not recorded | The assistant could not say which project was most relevant (facts held project titles only). | P5 | jeswinjarald-hash (sole Git author) | Logical | Profile-summary facts include project technologies. | 2026-10-10 | Closed | RESUME_PARSING_AUDIT.md #10; fix 4699c7c
D-11 | Not recorded | Not recorded | Refreshing Skill Gap, Customize or Interview Prep lost the selected opportunity. | P5 | jeswinjarald-hash (sole Git author) | User Interface | Job-scoped pages keep the opportunity in the URL (?job=). | 2026-10-10 | Closed | RESUME_PARSING_AUDIT.md #11; fix 4699c7c; unit routing.test.ts (feature branch)
D-12 | Not recorded | Not recorded | At 620 px or less only 5 of 10 destinations were reachable and the top bar overflowed a 375 px screen. | P5 | jeswinjarald-hash (sole Git author) | User Interface | Mobile navigation includes every destination and keeps the active item in view. | 2026-10-10 | Closed | UI_UX_POLISH_REPORT.md section 1 (P1); fix 4699c7c; e2e responsive.spec.ts (feature branch)
D-13 | Not recorded | Not recorded | Choosing a new file before uploading it cleared the active resume app-wide; after a failed re-upload old data could show. | P5 | jeswinjarald-hash (sole Git author) | Logical | Active resume kept until a new upload is accepted; stale data never shown for the new file. | 2026-10-10 | Closed | UI_UX_POLISH_REPORT.md section 1 (P1); fix 4699c7c; e2e resume-workflow.spec.ts
D-14 | Not recorded | Not recorded | A failed 'Save edits' in Customize Application was stored but never shown. | P5 | jeswinjarald-hash (sole Git author) | User Interface | Save errors rendered; unsaved-edits notice added. | 2026-10-10 | Closed | UI_UX_POLISH_REPORT.md section 1 (P1); fix 4699c7c
D-15 | Not recorded | Not recorded | Assistant conversation actions and version switching had no error handling (unhandled promise rejections). | P5 | jeswinjarald-hash (sole Git author) | Logical | All actions report errors; guarded version loading. | 2026-10-10 | Closed | UI_UX_POLISH_REPORT.md section 1 (P1); fix 4699c7c
D-16 | Not recorded | Not recorded | A 401 mid-session left pages on 'Authentication required.' with no route back; an unreachable backend was unexplained. | P5 | jeswinjarald-hash (sole Git author) | User Interface | Session-expired event returns to sign-in; unreachable state with retry. | 2026-10-10 | Closed | UI_UX_POLISH_REPORT.md section 1 (P1); fix 4699c7c
D-17 | Not recorded | Not recorded | Unbounded search similarity was displayed as 'N% relevance'. | P5 | jeswinjarald-hash (sole Git author) | User Interface | Raw score shown with an explanatory tooltip. | 2026-10-10 | Closed | UI_UX_POLISH_REPORT.md section 1 (P1); fix 4699c7c
D-18 | Not recorded | Not recorded | FastAPI 422 responses were rendered as '[object Object]'; raw validator text reached the sign-up form. | P5 | jeswinjarald-hash (sole Git author) | User Interface | apiDetailMessage gives readable messages (src/config/api.ts). | 2026-10-10 | Closed | UI_UX_POLISH_REPORT.md section 1 (P2); fix 4699c7c
D-19 | Not recorded | Not recorded | Accessibility: hidden file input, missing focus styles, no skip link or aria-current, sub-AA text contrast, 'OK'/'00' text icons. | P5 | jeswinjarald-hash (sole Git author) | Standards | Focusable input, focus styles, skip link, aria-current, contrast raised, icons replaced. | 2026-10-10 | Closed | UI_UX_POLISH_REPORT.md section 1 (P2); fix 4699c7c; e2e a11y/contrast specs (feature branch)
D-20 | Not recorded | Not recorded | Resume processing steps were not tied to the real requests (only the last step was ever active). | P5 | jeswinjarald-hash (sole Git author) | User Interface | Steps follow the real backend calls and are marked done only after each returns. | 2026-10-10 | Closed | UI_UX_POLISH_REPORT.md section 1 (P2); fix 4699c7c
D-21 | Not recorded | Not recorded | Session cookie was hard-coded secure=False. | P5 | jeswinjarald-hash (sole Git author) | Standards | Cookie is Secure whenever APP_ENV is not development, with SESSION_COOKIE_SECURE override. | 2026-10-10 | Closed | UI_UX_POLISH_REPORT.md section 1 (security); fix 4699c7c; test_session_cookie.py
D-22 | Not recorded | Not recorded | SQLite path resolved against the process working directory, so login failed after a restart from another folder. | P2 | jeswinjarald-hash (sole Git author) | Logical | resolve_backend_path() makes relative SQLite and storage paths resolve against backend/. | 2026-09-19 | Closed | Commit 2e16893 message; test_auth_persistence.py
D-23 | Not recorded | Not recorded | CORS preflight returned 400 and blocked /api/auth/me when the Vite dev port changed. | P3 | jeswinjarald-hash (sole Git author) | Logical | Any localhost port allowed only in development; configured FRONTEND_URL allowed exactly. | 2026-09-23 | Closed | Commit f202ca1 message; test_cors.py
D-24 | Not recorded | Not recorded | Real-world resumes produced dozens of one-word 'projects' and prose words as 'skills'. | P3 | jeswinjarald-hash (sole Git author) | Logical | Title/annotation detection ordering fixed; fragment merging; skills-list sanity cap; parser_warnings. | 2026-09-23 | Closed | MILESTONE_1.md robustness audit; fix 19af562; test_resume_parser_robustness.py, test_resume_parser_real_world.py
D-25 | Not recorded | Not recorded | M3.1 manual review: wrong project count, soft-skill matching, learning-only evidence counted, evidence noise. | P2 | jeswinjarald-hash (sole Git author) | Logical | Findings resolved in skill-gap evidence handling. | 2026-09-19 | Closed | Commit 509d53c message; test_skill_gap_evidence.py
D-26 | Not recorded | Not recorded | M3.2 output quality: unclean skills, long summary, unnatural cover letter. | P3 | jeswinjarald-hash (sole Git author) | Logical | Skill cleaning, concise summary, rewritten cover-letter template. | 2026-09-24 | Closed | Commit d4d3c49 message; test_customization_quality.py
D-27 | Not recorded | Not recorded | Card highlight was lost when React re-rendered the card's classes under a resting pointer. | P6 | jeswinjarald-hash (sole Git author) | User Interface | Highlight state preserved across class re-renders. | 2026-10-11 | Closed | Commit cd30486; e2e lighting.spec.ts (feature branch)
D-28 | Not recorded | Not recorded | Defect A: after session expiry and sign-in on the same URL, the selected job or application was cleared. | P6 | jeswinjarald-hash (sole Git author) | Logical | Selection restored from the URL after re-authentication. | 2026-10-11 | Closed | Fix 024a63d; e2e session-expiry.spec.ts (feature branch); detection date not recorded
D-29 | Not recorded | Not recorded | Defect B: search results must be a ranking with the raw score, never a percentage (whether this was a regression of D-17 is not recorded). | P6 | jeswinjarald-hash (sole Git author) | User Interface | Ranking with raw score; regression test added. | 2026-10-11 | Closed | Fix 024a63d; e2e resume-dependent.spec.ts (feature branch)
D-30 | Not recorded | Not recorded | Defect C: job details must show the score the backend calculated, and 'no score' (not zero) outside the retrieved set. | P6 | jeswinjarald-hash (sole Git author) | Logical | Score read from the match API; explicit no-score state; retry on error. | 2026-10-11 | Closed | Fix 024a63d; e2e resume-dependent.spec.ts (feature branch)
D-31 | Not recorded | Not recorded | Defect D: a new account's name and e-mail counted towards profile completion. | P6 | jeswinjarald-hash (sole Git author) | Logical | Completion counts only the 8 profile details the user saves. | 2026-10-11 | Closed | Fix 024a63d; e2e navigation.spec.ts, unit profileCompletion.test.ts (feature branch)
D-32 | Not recorded | Not recorded | Defect E: the learning-roadmap context could show the previous resume's data or be overwritten by a slow stale response. | P6 | jeswinjarald-hash (sole Git author) | Logical | Context reset on resume change; stale responses ignored; errors shown with retry. | 2026-10-11 | Closed | Fix 024a63d; e2e roadmap-lifecycle.spec.ts, resume-dependent.spec.ts (feature branch)
NOTE: Reconstructed on 2026-10-17 from audit reports, fix commits and regression tests; no defect tracker was kept during development. Submitter and detection date were not recorded. Action Taken Date is the date of the fixing commit. Phases P2-P6 are defined in MILESTONE_HISTORY.md.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others